## Sheet1
Perunding Ukur Tekun Sdn Bhd
MRT v207
Progress Report for Field Work as of 11th April 2017
Survey Works | [5 empty] | March | [8 empty] | April | [29 empty] | May
No. | Description | Total Quantity | Percentage Completion by Item | Percentage by item | Percentage Overall | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
1 | Control Point (25%) - Monumenting | 32 |  |  |  | March 23: 10; March 24: 10; March 25: 10; March 27: 10
|  | 32 | 100% | 33% |  | March 24: 11; March 25: 10; March 28: 4; April 3: 7
| - Traversing | 32 |  |  |  | March 28: 10; March 29: 10; March 30: 10; March 31: 10
| Required to redo | 32 | 100% | 33% |  | March 27: 21; March 31: 4; April 3: 7; April 7: recheck; April 8: recheck; April 11: recheck; April 12: recheck; April 13: recheck; April 14: recheck
| - Leveling | 32 |  |  |  | April 1: 10; April 3: 10; April 4: 10; April 5: 10
| Require to retake one more levelling | 32 | 100% | 34% | 25% | March 29: 14; March 30: 7; April 4: 7; April 5: 4; April 10: recheck; April 12: recheck; April 13: recheck; April 14: recheck
2 | Demarcation of Centre of Pier (25%) | 131 | [17 empty] | 6 | 12 | 18 |  | 24 | 30 | 36 | 42 | 48 | 54 |  | 60 | 66 | 72 | 78 | 84 | 90 |  | 96 | 102 | 108 | 114 | 120 | 126 |  | 131
|  | 0 | 0% |  | 0%
3 | Demarcation of ROW (25%) | 284 | [17 empty] | 12 | 24 | 36 |  | 48 | 60 | 72 | 84 | 96 | 108 |  | 120 | 132 | 144 | 156 | 168 | 180 |  | 192 | 204 | 226 | 238 | 240 | 252 |  | 264 | 276 | 284
|  | 118 | 41.55% |  | 10.39% | [14 empty] | 23 |  |  |  |  | 7 | 16 | 16 |  | 30 |  | 26
4 | Topographical Survey (25%) | 58 |  |  |  | 1.6 | 3.2 | 4.8 |  | 6.4 | 8 | 9.6 | 11.2 | 12.8 | 14.4 |  | 16 | 17.6 | 19.2 | 20.8 | 22.4 | 24 |  | 25.6 | 27.2 | 28.8 | 30.4 | 32 | 33.6 |  | 35.2 | 36.8 | 38.4 | 40 | 41.6 | 43.2 |  | 44.8 | 46.4 | 48 | 49.6 | 51.2 | 52.8 |  | 54.4 | 56 | 58
|  | 43.41 | 74.84% |  | 18.71% | 0 | 0 | 0 |  | 2.5 | 2.8 | 3.1 | 3.4 | 3.49 | 0 |  | 1.6 | 3.3 | 1.2 | 5.85 | 1 | 0 |  | 4.5 | 4.03 | 0 | 0.89 | 2.29 | 0.96 |  | 2.5
| Total Completion |  |  |  | 54.1%
UD Works | [6 empty] | March | [7 empty] | April
No. | Description | Total Quantity | Percentage Overall |  |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Utilities Detection | 193937 |  |  |  |  | 8000 | 16000 |  | 24000 | 32000 | 40000 | 48000 | 56000 | 64000 |  | 72000 | 80000 | 88000 | 96000 | 104000 | 112000 |  | 120000 | 128000 | 136000 | 144000 | 152000 | 160000 |  | 168000 | 176000 | 184000 | 193937
|  | 144278 | Total Completion |  | 74.39% |  | March 24: RAIN; March 25: 16771; March 27: 29685; March 28: 47399; March 29: 25801; March 30: 21219; April 17: 3403

## Sheet2
|  | OS101 | 2015 | OS - 2015 |  |  | OS101 | 2017 | OS - 2017 |  | JUPEM 2015 |  |  | JUPEM OLD
1 | 2 | 5.0149 | 5.014 | 0.0009 | 1 | 2 | 5.0149 | 5.012 | 0.0029 | 5.0149 | 5.014 | 0.0009 | 5.0149 | 5.011 | 0.0039
1 | 3 | 9.9982 | 9.995 | 0.0032 | 1 | 3 | 9.9982 | 9.993 | 0.0052 | 9.9982 | 9.995 | 0.0032 | 9.9982 | 9.991 | 0.0072
1 | 4 | 49.0047 | 49.001 | 0.0037 | 1 | 4 | 49.0047 | 49 | 0.0047 | 49.0047 | 49.001 | 0.0037 | 49.0047 | 48.996 | 0.0087
1 | 5 | 87.0003 | 86.997 | 0.0033 | 1 | 5 | 87.0003 | 86.996 | 0.0043 | 87.0003 | 86.997 | 0.0033 | 87.0003 | 86.994 | 0.0063
1 | 6 | 125.0117 | 125.008 | 0.0037 | 1 | 6 | 125.0117 | 125.008 | 0.0037 | 125.0117 | 125.008 | 0.0037 | 125.0117 | 125.002 | 0.0097
1 | 7 | 163.0057 | 163.001 | 0.0047 | 1 | 7 | 163.0057 | 163 | 0.0057 | 163.0057 | 163.001 | 0.0047 | 163.0057 | 162.995 | 0.0107
1 | 8 | 201.0158 | 201.01 | 0.0058 | 1 | 8 | 201.0158 | 201.009 | 0.0068 | 201.0158 | 201.01 | 0.0058 | 201.0158 | 201.002 | 0.0138
1 | 9 | 251.012 | 251.006 | 0.006 | 1 | 9 | 251.012 | 251.005 | 0.007 | 251.012 | 251.006 | 0.006 | 251.012 | 250.997 | 0.015
1 | 10 | 300.0387 | 300.029 | 0.0097 | 1 | 10 | 300.0387 | 300.03 | 0.0087 | 300.0387 | 300.029 | 0.0097 | 300.0387 | 300.003 | 0.0357
2 | 3 |  |  | 0 | 2 | 3 |  |  | 0 |  |  | 0 |  |  | 0
2 | 4 |  |  | 0 | 2 | 4 |  |  | 0 |  |  | 0 |  |  | 0
2 | 5 |  |  | 0 | 2 | 5 |  |  | 0 |  |  | 0 |  |  | 0
2 | 6 |  |  | 0 | 2 | 6 |  |  | 0 |  |  | 0 |  |  | 0
2 | 7 | 157.992 | 157.987 | 0.005 | 2 | 7 | 157.992 | 157.987 | 0.005 | 157.992 | 157.987 | 0.005 | 157.992 | 157.984 | 0.008
2 | 8 | 196.0021 | 195.996 | 0.0061 | 2 | 8 | 196.0021 | 195.995 | 0.0071 | 196.0021 | 195.996 | 0.0061 | 196.0021 | 195.991 | 0.0111
2 | 9 | 245.9979 | 245.992 | 0.0059 | 2 | 9 | 245.9979 | 245.991 | 0.0069 | 245.9979 | 245.992 | 0.0059 | 245.9979 | 245.986 | 0.0119
2 | 10 | 295.0257 | 295.015 | 0.0107 | 2 | 10 | 295.0257 | 295.016 | 0.0097 | 295.0257 | 295.015 | 0.0107 | 295.0257 | 294.992 | 0.0337
|  |  |  | 0.0687 |  |  |  |  | 0.0777 | 2086.1197 | 2086.051 | 0.0687 |  |  | 0.1757
|  |  | cerapan | 0.0052846 |  |  |  | cerapan | 0.0059769

## Sheet3
| March | [8 empty] | April | [29 empty] | May
| 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
chong | 0 | 0 | 0 |  | 2.5 | 2.8 | 3.1 | 3.4 |  |  |  | 1.6 | 3.3 | 1.2 | 1.2 | 1 | 0 |  | 4.5 | 2.88 | 0.44 | 0.45 | 0.97 | 0.96 |  | 2.5
foo | [8 empty] | 3.49 | [5 empty] | 4.65 |  | 0 |  |  | 1.15 |  |  | 1.32
total | 0 | 0 | 0 | 0 | 2.5 | 2.8 | 3.1 | 3.4 | 3.49 | 0 | 0 | 1.6 | 3.3 | 1.2 | 5.85 | 1 | 0 | 0 | 4.5 | 4.03 | 0.44 | 0.45 | 2.29 | 0.96 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.41
| March | [8 empty] | April | [29 empty] | May
| 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
hui | [14 empty] | 23 | [8 empty] | 30 |  | 26
haris | [19 empty] | 7 | 16 | 16
total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 7 | 16 | 16 | 0 | 30 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118