## Sheet1
HighPark Gamuda Kelana Jaya
1 | Preparatory work which involve serach and purchase Certified plan from survey department
2 | Mobilization and demobilization of survey team to the site
3 | Planimetric control and connection to the nearest boundary mark and old reference mark | 1500
4 | Control levelling from nearest proven TBM / BM and bringing its heights to the site | 500
5 | Establishment of 2 TBMs on permanent structure within site for future reference | 500
6 | Demarcation Survey | 500
7 | Check Pre-comp Plan, peparation of pre-comp plan with building grid line setting out plan and submit to the client for their project architech comment
8 | As-built and checking existing completed structure
a | Prepare as built survey plan of the existing completed Column and Lift Pit on level Basement 1 | 2500
Reference Gridline and Marks.
9 | Setting out survey for 6 NOS of building griline intersection points For:
a | 6 Level Podium ( rm1000 * 6) | 6000
b | 3 Level Shop Lots (RM1000*3) | 3000
c | Tower A (1 Level) | 1000
d | Tower B (1 Level) | 1000
Verticallity Control points
10 | Transfer of 4 NOS control point at every 3 floor interval for:
a | Tower A (9 floor) 4,Flr7Flr,10Flr,13Flr,16Flr,19Flr,22Flr,25Flr,27Flr (rm1000*9) | 9000
b | Tower B (9 floor) 4,Flr7Flr,10Flr,13Flr,16Flr,19Flr,22Flr,25Flr,27Flr (rm1000*9) | 9000
11 | Verticallity Checking
a | Prepare as built survey plan of the existing completed Column and Lift Pit on level 1 - 6(RM2500 * 6) | 15000
b | Prepare as built survey plan of the existing 10 NOS selected completed Shear Wall and Lift Wall on level Soho 7 -33 (RM1000*27) | 27000
12 | Settlement Checking
a | Establishment 30 NOS monitoring settlement marker groung floor column | 2000
b | Monitoring Survey of building settlement at every month interval (accuraancy 0.1mm decimal) - 48 trips within 48 month (RM1000*48) | 48000
13 | As built Survey
a | Carried out As buit survey upon completion of all building and infa work. Pick up existing building outline, drain, road, sewer manhole. | 1500
128000