d.c.a.

Design Collective Architecture Network Sdn.Bhd. (Co.No. 550431H)
in association with Design Collective Architects    (LAM Reg. No. P/D 9)

No. 57,  Jalan SS 22/19,  Damansara Jaya,  47400 Petaling Jaya,  Selangor,  Malaysia

Tel:   +603 7727 0199          +603 7727 2199            Fax: +603 7722 3199


CERTIFICATE of PAYMENT #9
Job ref: DCA/106/COP9
Date: 31st October 2022
THE SECRETARY OF THE TRUSTEES OF THE METHODIST CHURCH IN MALAYSIA,

PROJECT:

CADANGAN TAMBAHAN DAN PINDAAN KEPADA SEBUAH GEREJA DUA TINGKAT SEDIA ADA DAN SATU UNIT TEMPAT PEMBUANGAN SAMPAH DI NO.7, PERSIARAN ANGGERIK VANILLA, SEKSYEN 31, 40460 SHAH ALAM, SELANGOR DARUL EHSAN UNTUK TETUAN

THE SECRETARY OF THE TRUSTEES OF THE METHODIST CHURCH IN MALAYSIA.
Awarded Contract Sum:






RM
   1,680,000.00
Variation works:

VO Addition:




RM
             -
VO Omission:




RM

-

Nett Variation Works






RM
             -
TOTAL CONTRACT SUM:





RM
  1,680,000.00

Liquidated & Ascertained Damages
Sectional Completion - Temporary Toilet
RM
  350.00 per day

Overall Completion


RM        1,500.00 per day

Max Retention Sum



RM      84,000.00

We hereby certify that under the terms of the building contract, the sum of Ringgit : 

Two Hundred Seventy-Nine Thousand One Hundred Forty-Two and Cents Fifty-Two only 
(RM 279,142.52)
is now due to:

NSK CONSTRUCTION & ENGINEERING SDN. BHD.

B-2-6, BBT One Boulevard, 

Lebuh Batu Nilam 2,
Bandar Bukit Tinggi, 

41200 Klang, Selangor. 
Tel: 03-3325 2328/ 03-3325 2628
Fax: 03-3325 2168
Email: enquiry@nskce.com
1.0 Main Contractor 

a. Value of Work Done





RM
  1,302,250.83


             b. Value of Materials on-site




RM
            -
c. Variation Works





RM
            -

2.0 NSC


a. Value of Work Done by NSC




RM
            -
3.0 Less

a. Retention Fund (10%) (Limit of 5% of contract sum)

RM
    (84,000.00) 
b. Utility Bills 






RM
            -
c. Previous Payment 





RM
  (939,108.31)







Amount payable by this certificate:




RM
   279,142.52
Please make payment direct to the Contractor within 30 days from the date of the Certificate of Payment and advise us by sign and   returning the copy of this certificate when you have done so.

________________________

(Ar. Chan Weng Cheong)

Date: 31st October 2022
